## Yearly Plan
Quarter | Goals | Start | End | Status
Quarter 1 | Project milestone sample 1 | 2024-01-01 | 2024-03-31 | Done
Quarter 2 | Project milestone sample 2 | 2024-04-01 | 2024-06-30 | Done
Quarter 3 | Project milestone sample 3 | 2024-07-01 | 2024-09-30 | Inprogress
Quarter 4 | Project milestone sample 4 | 2024-10-01 | 2024-12-31 | To do

## Quater 1 Plan
Quarter 1 | Project milestone sample 1
Week | backend | complexcity | estimation | frontend | complexcity | estimation | Status
2024-01-01 | build data model feature 1 | High | 5 | build UI feature 1 | High | 5 | Done
2024-01-08 | build API feature1 | High | 5 | Integrate with BE feature 1 | High | 5 | Done
2024-01-15 | Unit test | High | 5 | Unit test | High | 5 | Done
2024-01-22 | Test CI/CD | High | 5 | Test CI/CD | High | 5 | Done
2024-01-29 | build data model feature 1 | High | 5 | build UI feature 1 | High | 5 | Done
2024-02-05 | build API feature1 | High | 5 | Integrate with BE feature 1 | High | 5 | Done
2024-02-12 | Unit test | High | 5 | Unit test | High | 5 | Done
2024-02-19 | Test CI/CD | High | 5 | Test CI/CD | High | 5 | Done
2024-02-26 | Ready for QA | High | 5 | Ready for QA | High | 5 | Done
2024-03-04 | demostration | Medium | 1 | demostration | Medium | 1 | Done
2024-03-11
2024-03-18
| Goals |  |  | Goals
| Complete feature 1 |  |  | Complete feature 1
| Complete demostration for feature 1 |  |  | Complete demostration for feature 1
Formulas:
Week = [Week, row above]+7